## Project Planner
Inividual Project - Plan
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Research Areas of Parenting | 1 | 3 | 1 | 6 | 100%
Literature Review | 1 | 8 | 2 | 7 | 100%
Choose Activation Points | 3 | 1 | 3 | 2 | 100%
Create Listening abitily | 8 | 2 | 8 | 2 | 100%
Storing of Data | 10 | 3 | 10 | 3 | 100%
Processing of Input Data | 14 | 1 | 13 | 1 | 100%
Activate on Decibel Level Reached | 12 | 4 | 14 | 3 | 100%
Continue Listening as More Sound Heard | 14 | 1 | 15 | 1 | 100%
Add Sounds Heard Before Shouting | 15 | 2 | 16 | 3 | 100%
Moving Talking Window as More Heard | 17 | 2 | 19 | 2 | 75%
Research Exporting to External Devices | 21 | 1 | 21 | 1 | 100%
Create Ability on Found Framework | 22 | 3 | 22 | 3 | 50%
Export to Raspberry Pi | 25 | 2 | 25 | 1 | 100%
Upload Files to Dropbox | 27 | 2 | 26 | 2 | 100%
Feedback to Users (Feedback can added to Dropbox file) | 25 | 2 | 26 | 2 | 100%
Test | 26 | 2 | 26 | 2 | 100%
Research Methods of Intervention | 26 | 1 | 0 | 0 | 0%